## Sheet1
Risk Category | Impact | Probability | Mitigation Complexity | Final Score | Rank | Risk Level | Why It Matters | MVP Mitigation (Anodiam-Led)
Asset Theft & Damage | 4 | 4 | 4 | 4 | 2 | 🔴 High | E-bikes are high-value assets; owner trust is critical | KYC (owner & renter), GPS tracking, trip logs, photo check-in/out, security deposits
Insurance & Liability | 5 | 4 | 5 | 4 | 2 | 🔴 High | Accidents can kill platform adoption | Per-ride insurance option, digital waivers, incident reporting flow
Marketplace Cold-Start | 4 | 5 | 4 | 5 | 1 | 🟠 Medium-High | Two-sided marketplace adoption risk | Hyper-local UNSW launch, early owner incentives, verified profiles & ratings
Payment Fraud & Chargebacks | 5 | 4 | 5 | 4 | 2 | 🟠 Medium | Financial leakage threatens unit economics | Stripe escrow, pre-authorised deposits, fraud scoring, booking limits
Battery Abuse & Maintenance | 3 | 4 | 3 | 4 | 2 | 🟡 Medium-Low | Owner long-term cost concerns | Usage analytics, battery health reporting, misuse flagging
Regulatory Compliance (NSW) | 5 | 3 | 4 | 3.75 | 3 | 🟠 Medium | Council rules can block scaling | Platform-as-facilitator model, speed compliance, in-app safety prompts
Technical Complexity | 4 | 2 | 4 | 2 | 6 | 🟡 Medium-Low | Overbuilding delays validation | Strict MVP scope, modular APIs, hardware-agnostic design
Demand & Unit Economics | 4 | 3 | 5 | 2.4 | 4 | 🟡 Medium-Low | Must beat fleet rentals on value | Long-duration rentals, tourist/student focus, utilisation tracking
Founder Execution Risk | 3 | 3 | 4 | 2.25 | 5 | 🟡 Medium-Low | First-time founder credibility | Anodiam as technical & product partner
Scalability (Post-PMF) | 2 | 3 | 3 | 2 | 6 | 🟢 Low (Now) | Only relevant after traction | Cloud-native backend, city-based rollout